## Package 7 BOQ
PACKAGE 7 | [5 empty] | MAIN CONTRACTOR
CONTRACT N3TC/RM-2025-607: Vaal River to the Heidelberg S IC_N3-10 km 0 to N3-11 km 15.1 | [5 empty] | N3-10 km 24 to N3-10 km 45.8
MOWING, CUTTING AND REMOVAL OF VEGETATION ON THE N3 – PACKAGE 7
PART 1.1 MANAGEMENT |  |  |  |  | Main Contractor
ITEM NO |  | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
TENDERERS TO REFER TO THE PRICING INSTRUCTIONS
M0300 |  | CONTRACTOR'S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS
M030.01 |  | Fixed Obligations | Lump Sum | 1 |  | 0
Payment of the Lump Sum shall be as follows:
50% on commencement of the contract.
35% when contract period reaches half of the contract period.
15% on completion of the contract.
PM030.03 |  | Period Related Obligation
(Payment pro-rata to value of work done in Period)
| (a) | General Mow.
|  | (i) Cycle 1 General mow April to June 2026 | Period | 1 |  | 0
|  | (ii) Cycle 2 General mow April to June 2027 | Period | 1 |  | 0
| (b) | Shoulder Mow.
|  | (i) Cycle 1: Shoulder mow November to December 2025 | Period | 1 |  | 0
|  | (ii) Cycle 1: Shoulder Mow January to February 2026 | Period | 1 |  | 0
|  | (iii) Cycle 1: Shoulder mow November to December 2026 | Period | 1 |  | 0
|  | (iv) Cycle 2: Shoulder Mow January to February 2027 | Period | 1 |  | 0
|  | (v) Cycle 2: Shoulder Mow November to December 2027 | Period | 1 |  | 0
PM030.09 | (a) | All Occupational health and safety obligations including that of EME Subcontractors | Prov Sum | 1 | 15000 | 15000
| (b) | The Contractor's overhead charges and profit in respect of sub-item PM030.09 (a) | % | 15000 |  | 0
PM020.06 |  | Training
Including Main Contractor plus EME sub-contractors as instructed by the Employer
| (a) | Safety | Prov Sum | 1 | 15000 | 15000
| (b) | Remuneration of workers undergoing training | Prov Sum | 1 | 14200 | 14200
| (c) | The Contractor's overhead charges and profit in respect of sub-item PM020.06 (a) & (b) above | % | 29200 |  | 0
NOTE.
1. The rate paid for workers undergoing training shall be R40 per hour, which includes all costs including transport, meals and other subsistence.
2. The daily rate shall be based on a max six (6) hrs for class room training and eight (8) hrs for practical training
3. The contractor shall nominate per training category. 2 persons from Main Contractor and 1 each from EME sub-contractors.
4. N3TC shall cover the cost of the training and materials if applicable as well as the venue.
44200
CARRIED FORWARD TO NEXT PAGE
CONTRACT N3TC/RM-2025-607: Vaal River to the Heidelberg S IC_N3-10 km 0 to N3-11 km 15.1 | [5 empty] | MAIN CONTRACTOR
MOWING, CUTTING AND REMOVAL OF VEGETATION ON THE N3 – PACKAGE 7 | [5 empty] | N3-10 km 24 to N3-10 km 45.8
PART 1.1 MANAGEMENT (continued)
ITEM NO |  | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | BROUGHT FORWARD FROM PREVIOUS PAGE |  |  |  | 44200
PM0500 |  | ACCOMMODATION OF TRAFFIC
PM050.01 |  | Accommodation of Traffic
| (a) | Provision of temporary traffic control facilities. | Lump Sum | 1 |  | 0
This Item is for the payment of all road signs required by the Main Contractor and EME Sub-Contractors for the duration of the Contract namely 26 months
The Main Contractor shall issue the required road signs to the EME Sub-Contractors at the commencement of each mowing Period.
The Main Contractor shall be responsible for the maintenance and safe keeping of all road signs for the duration of the Contract, namely 26 months.
The life of the signs is deemed to be the Duration of the contract, namely 26 months.
The minimum Tenderer Rate for Item PM050.01 (a) shall be R20,000.00.
This is to ensure adequate provision for required signs, in particular should the Contractor request the Employer to assist in procuring the signs under this item.
| (b) | Deduct item should the Contractor request the Employer to assist in purchasing the required road signs. | PC Sum |  | 20000 | Rate Only
The amount to be deducted shall be the actual cost price of the road signs purchased by the Employer at the request of the Contractor.
PM6120 |  | MANAGEMENT OF EME SUB-CONTRACTORS
PM612.01 |  | Handling Fee payable for management of subcontractors
|  | Contractor to tender a percentage mark-up on the value of the EME work done as a fee for the management of sub-contractors | % | 372300 |  | 0
Calculation of the Management Fee for the Tender.
The "QUANTITY" for this item shall be determined by inserting the Total for the Scheduled Works by EME Sub-Contractors from the Summary Page below sub-Total Part 2
Multiply this sub-Total be the tendered management fee to obtain the total tendered amount for Management Fee.
The minimum Tenderer Rate for Item PM612.01 shall be 5%.
|  | TOTAL PART 1.1: MANAGEMENT CARRIED TO SUMMARY |  |  |  | 44200
CONTRACT N3TC/RM-2025-607: Vaal River to the Heidelberg S IC_N3-10 km 0 to N3-11 km 15.1 | [5 empty] | MAIN CONTRACTOR
MOWING, CUTTING AND REMOVAL OF VEGETATION ON THE N3 – PACKAGE 7 | [5 empty] | N3-10 km 24 to N3-10 km 45.8
PART 1.2: OPERATIONAL
ITEM NO |  | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
PM0500 |  | ACCOMMODATION OF TRAFFIC
PM050.03 |  | Accommodation of traffic and maintaining temporary deviations.
Main Contractor. Measured per period
Payment pro-rata to value of work done in Period
| (a) | General Mow.
|  | (i) Cycle 1 General mow April to June 2026 | Period | 1 |  | 0
|  | (ii) Cycle 2 General mow April to June 2027 | Period | 1 |  | 0
| (b) | Shoulder Mow.
|  | (i) Cycle 1: Shoulder mow November to December 2025 | Period | 1 |  | 0
|  | (ii) Cycle 1: Shoulder Mow January to February 2026 | Period | 1 |  | 0
|  | (iii) Cycle 1: Shoulder mow November to December 2026 | Period | 1 |  | 0
|  | (iv) Cycle 2: Shoulder Mow January to February 2027 | Period | 1 |  | 0
|  | (v) Cycle 2: Shoulder Mow November to December 2027 | Period | 1 |  | 0
M6100 |  | CONTROLLING VEGETATION GROWTH: MOWING AND CUTTING
PM610.01 |  | Shoulder mowing and removal of grass cuttings
(Mowing of interchanges is measured separately)
| (a) | Reserve with dual carriageway, min width 3m including full median width, excluding interchanges. Including baling/removal. | km | 109 |  | 0
| (b) | Reserve with single carriageway, min width 3m excluding interchanges. Including baling/removal. | km |  |  | Rate Only
| (d) | Ad hoc cutting of the median outside of the shoulder and general mow periods on instruction of the engineer | Prov Sum | 1 | 100000 | 100000
M6100 |  | CARRIED FORWARD TO NEXT PAGE |  |  |  | 100000
CONTRACT N3TC/RM-2025-607: Vaal River to the Heidelberg S IC_N3-10 km 0 to N3-11 km 15.1 | [5 empty] | MAIN CONTRACTOR
MOWING, CUTTING AND REMOVAL OF VEGETATION ON THE N3 – PACKAGE 7 | [5 empty] | N3-10 km 24 to N3-10 km 45.8
PART 1.2 : OPERATIONAL (continued)
ITEM NO |  | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | BROUGHT FORWARD FROM PREVIOUS PAGE |  |  |  | 100000
PM610.02 |  | General mowing of the full road reserve
(Removal of grass cuttings and or baling measured separately)
(General mowing of interchanges is measured separately)
| (a) | General mow reserve with dual carriageway, excluding interchanges | km | 43.6 |  | 0
| (c) | General mow interchanges | No | 7 |  | 0
Refer to Table in Section C4.1.2.4
| (d) | Extra over item PM610.02 (a) for baling and or removal of grass cuttings from reserve with dual carriageway | km | 43.6 |  | 0
| (f) | Extra over item PM610.02 (c) for baling and or removal of grass cuttings from interchanges | No | 7 |  | 0
| (g) | Baling and Removal of cut grass from the road reserve or interchanges where the grass is mowed by others
| (i) | From reserve with dual carriageway | km | Rate only |  | Rate Only
| (ii) | From reserve with single carriageway | km | Rate only |  | Rate Only
| (iii) | From interchanges | No | Rate only |  | Rate Only
The rates tendered under this "Rate Only" item shall not exceed the rate tendered for items PM610.02 (d), (e) & (f) respectively by more than 30%.
PM611.01 |  | Cutting of designated areas on the instruction of the Engineer | Prov Sum | 1 | 30000 | 30000
|  | TOTAL PART 1.2 MAIN CONTRACTOR OPERATIONAL CARRIED TO SUMMARY |  |  |  | 130000
CONTRACT N3TC/RM-2025-607: Vaal River to the Heidelberg S IC_N3-10 km 0 to N3-11 km 15.1 | [5 empty] | MAIN CONTRACTOR
MOWING, CUTTING AND REMOVAL OF VEGETATION ON THE N3 – PACKAGE 7 | [5 empty] | N3-10 km 24 to N3-10 km 45.8
SUMMARY OF BILL OF QUANTITIES AND CALCULATION OF THE TENDER SUM
SECTION |  | DESCRIPTION |  |  |  | AMOUNT
PART 1.1 |  | MANAGEMENT SECTION (MAIN CONTRACTOR) |  |  |  | 44200
|  | SUB-TOTAL PART 1.1 : MANAGEMENT SECTION |  |  |  | 44200
PART 1.2 |  | OPERATIONAL SECTION (MAIN CONTRACTOR) |  |  |  | 130000
|  | SUB-TOTAL PART 1.2 : OPERATIONAL SECTION |  |  |  | 130000
PART 2 |  | WORK BY EME SUBCONTRACTORS
PART 2.1 EME 1 |  | TOTAL VALUE OF SCHEDULE 2.1 - EME 1 BOQ | Total brought forward from EME 1 |  |  | 124100
PART 2.2 EME 2 |  | TOTAL VALUE OF SCHEDULE 2.2 - EME 2 BOQ | Total brought forward from EME 2 |  |  | 124100
PART 2.3 EME 3 |  | TOTAL VALUE OF SCHEDULE 2.4 - EME 4 BOQ | Total brought forward from EME 4 |  |  | 124100
SUB-TOTAL PART 2 : WORK FOR SUBCONTRACTORS CARRIED FORWARD TO ITEM "PM 612.01" QUANTITY COLUMN | [5 empty] | 372300
| SUB-TOTAL PART 1.1 : MANAGEMENT SECTION |  |  |  |  | 44200
| SUB-TOTAL PART 1.2: OPERATIONAL SECTION |  |  |  |  | 130000
| SUB-TOTAL PART 2 : WORK FOR SUBCONTRACTORS |  |  |  |  | 372300
SUB-TOTAL SCHEDULE A | [5 empty] | 546500
VAT AT 15% | [5 empty] | 81975
TOTAL TENDER SUM CARRIED FORWARD TO FORM OF OFFER | [5 empty] | 628475
628475
PACKAGE 7 | [5 empty] | EME 1
CONTRACT N3TC/RM-2025-607: Vaal River to the Heidelberg S IC_N3-10 km 0 to N3-11 km 15.1 | [5 empty] | N3-10 km 0 to N3-10 km 12
MOWING, CUTTING AND REMOVAL OF VEGETATION ON THE N3 – PACKAGE 7
PART 2.1: EME 1
ITEM NO |  | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
M0300 |  | CONTRACTOR'S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS
PM030.03 |  | Period Related Obligation
(Payment pro-rata to value of work done in Period)
| (a) | General Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1 General mow April to June 2026 | Period | 1 | 9800 | 9800
|  | (ii) Cycle 2 General mow April to June 2027 | Period | 1 | 9800 | 9800
| (b) | Shoulder Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1: Shoulder mow November to December 2025 | Period | 1 | 6200 | 6200
|  | (ii) Cycle 1: Shoulder Mow January to February 2026 | Period | 1 | 6200 | 6200
|  | (iii) Cycle 1: Shoulder mow November to December 2026 | Period | 1 | 6200 | 6200
|  | (iv) Cycle 2: Shoulder Mow January to February 2027 | Period | 1 | 6200 | 6200
|  | (v) Cycle 2: Shoulder Mow November to December 2027 | Period | 1 | 6200 | 6200
PM0500 |  | ACCOMMODATION OF TRAFFIC
The required road signs will be provided by the Main Contractor
PM050.03 |  | Accommodation of traffic and maintaining temporary deviations. Measured per period
The Employer has fixed rates under Item PM050.03 (a) and (b)
Payment shall be pro-rata to value of work done in Period
| (a) | General Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1 General mow April to June 2026 | Period | 1 | 12250 | 12250
|  | (ii) Cycle 2 General mow April to June 2027 | Period | 1 | 12250 | 12250
| (b) | Shoulder Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1: Shoulder mow November to December 2025 | Period | 1 | 9800 | 9800
|  | (ii) Cycle 1: Shoulder Mow January to February 2026 | Period | 1 | 9800 | 9800
|  | (iii) Cycle 1: Shoulder mow November to December 2026 | Period | 1 | 9800 | 9800
|  | (iv) Cycle 2: Shoulder Mow January to February 2027 | Period | 1 | 9800 | 9800
|  | (v) Cycle 2: Shoulder Mow November to December 2027 | Period | 1 | 9800 | 9800
NOTE: The Part 2.1 EME Contractor rates for Items PM610.01 and PM610.02 shall be the same as the rates tendered by the Main Contractor for the respective Items.
Therefore the rates tendered under the items in Part 1.2 shall be transferred to the respective items in this Schedule for Part 2.1.
M6100 |  | CONTROLLING VEGETATION GROWTH: MOWING AND CUTTING
PM610.01 |  | Shoulder mowing and removal of grass cuttings
(Mowing of interchanges is measured separately)
| (a) | Reserve with dual carriageway, min width 3m including full median width, excluding interchanges. Including baling/removal. | km | 60 | 0 | 0
PM610.02 |  | General mowing of the full road reserve
(Removal of grass cuttings and or baling measured separately)
(General mowing of interchanges is measured separately)
| (a) | General mow reserve with dual carriageway including the full median width, excluding interchanges | km | 24 | 0 | 0
| (c) | General mow interchanges | No | 7 | 0 | 0
Refer to Table in Section C4.1.2.4
| (d) | Extra over item PM610.02 (a) for baling and or removal of grass cuttings from reserve with dual carriageway | km | 24 | 0 | 0
| (f) | Extra over item PM610.02 (c) for baling and or removal of grass cuttings from interchanges | No | 7 | 0 | 0
TOTAL SCHEDULE 2.1 CARRIED FORWARD TO SUMMARY SCHEDULE MAIN CONTRACTOR BOQ - PART 2 |  |  |  |  | EME 1 | 124100
PACKAGE 7 | [5 empty] | EME 2
CONTRACT N3TC/RM-2025-607: Vaal River to the Heidelberg S IC_N3-10 km 0 to N3-11 km 15.1 | [5 empty] | N3-10 km 12 to N3-10 km 24
MOWING, CUTTING AND REMOVAL OF VEGETATION ON THE N3 – PACKAGE 7
PART 2.2: EME 2
ITEM NO |  | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
M0300 |  | CONTRACTOR'S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS
PM030.03 |  | Period Related Obligation
(Payment pro-rata to value of work done in Period)
| (a) | General Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1 General mow April to June 2026 | Period | 1 | 9800 | 9800
|  | (ii) Cycle 2 General mow April to June 2027 | Period | 1 | 9800 | 9800
| (b) | Shoulder Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1: Shoulder mow November to December 2025 | Period | 1 | 6200 | 6200
|  | (ii) Cycle 1: Shoulder Mow January to February 2026 | Period | 1 | 6200 | 6200
|  | (iii) Cycle 1: Shoulder mow November to December 2026 | Period | 1 | 6200 | 6200
|  | (iv) Cycle 2: Shoulder Mow January to February 2027 | Period | 1 | 6200 | 6200
|  | (v) Cycle 2: Shoulder Mow November to December 2027 | Period | 1 | 6200 | 6200
PM0500 |  | ACCOMMODATION OF TRAFFIC
The required road signs will be provided by the Main Contractor
PM050.03 |  | Accommodation of traffic and maintaining temporary deviations. Measured per period
The Employer has fixed rates under Item PM050.03 (a) and (b)
Payment shall be pro-rata to value of work done in Period
| (a) | General Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1 General mow April to June 2026 | Period | 1 | 12250 | 12250
|  | (ii) Cycle 2 General mow April to June 2027 | Period | 1 | 12250 | 12250
| (b) | Shoulder Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1: Shoulder mow November to December 2025 | Period | 1 | 9800 | 9800
|  | (ii) Cycle 1: Shoulder Mow January to February 2026 | Period | 1 | 9800 | 9800
|  | (iii) Cycle 1: Shoulder mow November to December 2026 | Period | 1 | 9800 | 9800
|  | (iv) Cycle 2: Shoulder Mow January to February 2027 | Period | 1 | 9800 | 9800
|  | (v) Cycle 2: Shoulder Mow November to December 2027 | Period | 1 | 9800 | 9800
NOTE: The Part 2.2 EME Contractor rates for Items PM610.01 and PM610.02 shall be the same as the rates tendered by the Main Contractor for the respective Items.
Therefore the rates tendered under the items in Part 1.2 shall be transferred to the respective items in this Schedule for Part 2.2.
M6100 |  | CONTROLLING VEGETATION GROWTH: MOWING AND CUTTING
PM610.01 |  | Shoulder mowing and removal of grass cuttings
(Mowing of interchanges is measured separately)
| (a) | Reserve with dual carriageway, min width 3m including full median width, excluding interchanges. Including baling/removal. | km | 60 | 0 | 0
PM610.02 |  | General mowing of the full road reserve
(Removal of grass cuttings and or baling measured separately)
(General mowing of interchanges is measured separately)
| (a) | General mow reserve with dual carriageway including the full median width, excluding interchanges, | km | 24 | 0 | 0
| (d) | Extra over item PM610.02 (a) for baling and or removal of grass cuttings from reserve with dual carriageway | km | 24 | 0 | 0
TOTAL SCHEDULE 2.1 CARRIED FORWARD TO SUMMARY SCHEDULE MAIN CONTRACTOR BOQ - PART 2 |  |  |  |  | EME 2 | 124100
PACKAGE 7
CONTRACT N3TC/RM-2025-607: Vaal River to the Heidelberg S IC_N3-10 km 0 to N3-11 km 15.1 | [5 empty] | EME 3
MOWING, CUTTING AND REMOVAL OF VEGETATION ON THE N3 – PACKAGE 7 | [5 empty] | N3-10 km 45.8 to N3-11 km 15.1
PART 2.3: EME 3
ITEM NO |  | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
M0300 |  | CONTRACTOR'S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS
PM030.03 |  | Period Related Obligation
(Payment pro-rata to value of work done in Period)
| (a) | General Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1 General mow April to June 2026 | Period | 1 | 9800 | 9800
|  | (ii) Cycle 2 General mow April to June 2027 | Period | 1 | 9800 | 9800
| (b) | Shoulder Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1: Shoulder mow November to December 2025 | Period | 1 | 6200 | 6200
|  | (ii) Cycle 1: Shoulder Mow January to February 2026 | Period | 1 | 6200 | 6200
|  | (iii) Cycle 1: Shoulder mow November to December 2026 | Period | 1 | 6200 | 6200
|  | (iv) Cycle 2: Shoulder Mow January to February 2027 | Period | 1 | 6200 | 6200
|  | (v) Cycle 2: Shoulder Mow November to December 2027 | Period | 1 | 6200 | 6200
PM0500 |  | ACCOMMODATION OF TRAFFIC
The required road signs will be provided by the Main Contractor
PM050.03 |  | Accommodation of traffic and maintaining temporary deviations. Measured per period
The Employer has fixed rates under Item PM050.03 (a) and (b)
Payment shall be pro-rata to value of work done in Period
| (a) | General Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1 General mow April to June 2026 | Period | 1 | 12250 | 12250
|  | (ii) Cycle 2 General mow April to June 2027 | Period | 1 | 12250 | 12250
| (b) | Shoulder Mow. (Fixed Rate by Employer)
|  | (i) Cycle 1: Shoulder mow November to December 2025 | Period | 1 | 9800 | 9800
|  | (ii) Cycle 1: Shoulder Mow January to February 2026 | Period | 1 | 9800 | 9800
|  | (iii) Cycle 1: Shoulder mow November to December 2026 | Period | 1 | 9800 | 9800
|  | (iv) Cycle 2: Shoulder Mow January to February 2027 | Period | 1 | 9800 | 9800
|  | (v) Cycle 2: Shoulder Mow November to December 2027 | Period | 1 | 9800 | 9800
NOTE: The Part 2.3 EME Contractor rates for Items PM610.01 and PM610.02 shall be the same as the rates tendered by the Main Contractor for the respective Items.
Therefore the rates tendered under the items in Part 1.2 shall be transferred to the respective items in this Schedule for Part 2.3.
M6100 |  | CONTROLLING VEGETATION GROWTH: MOWING AND CUTTING
PM610.01 |  | Shoulder mowing and removal of grass cuttings
(Mowing of interchanges is measured separately)
| (a) | Reserve with dual carriageway, min width 3m excluding interchanges. Including baling/removal. | km | 58.5 | 0 | 0
| (b) | Reserve with single carriageway, min width 3m excluding interchanges. Including baling/removal. | km |  | 0 | Rate Only
PM610.02 |  | General mowing of the full road reserve
(Removal of grass cuttings and or baling measured separately)
(General mowing of interchanges is measured separately)
| (a) | General mow reserve with dual carriageway including the full median width, excluding interchanges | km | 23.4 | 0 | 0
| (c) | General mow interchanges | No | 3.5 | 0 | 0
Refer to Table in Section C4.1.2.4
| (d) | Extra over item PM610.02 (a) for baling and or removal of grass cuttings from reserve with dual carriageway | km | 23.4 | 0 | 0
| (f) | Extra over item PM610.02 (c) for baling and or removal of grass cuttings from interchanges | No | 3.5 | 0 | 0
TOTAL SCHEDULE 2.1 CARRIED FORWARD TO SUMMARY SCHEDULE MAIN CONTRACTOR BOQ - PART 2 |  |  |  |  | EME 3 | 124100